Table of Contents

# CIS454 — Master Study Guide

Living document — updated as new course materials are added. Last updated after: Core_Scrum.pdf, CIS454_PP_Ch1.pptx, CIS454_PP_Ch2.pptx, CIS454_PP_Scrum_Ch_1.pptx

Format note: terms are defined inline the first time they’re used in a bullet, rather than in a separate glossary.

## CHAPTER 1: Introduction to Systems Analysis and Design

### Learning Objectives

- Understand the systems development life cycle (SDLC) — the standard set of phases every information system project moves through, from the initial idea to a working, supported system: the purpose of each of the four phases, the steps within each, and how the phases relate to one another.

- Identify project team roles in systems analysis and design (the different job functions people fill on a project team).

- Discuss criteria for choosing between Waterfall (a strict, one-pass-through-the-phases approach) and Agile/Scrum (an iterative, adaptive approach — both defined in detail below).

### The SDLC — Four Phases

1. Planning — “Why should we build this system?”

- Project Initiation: the formal kickoff of a project.

  - Develop a system request — the formal document that asks the organization to commit resources to a project (its parts are detailed in Chapter 2).

  - Conduct a feasibility analysis — a study of whether the project is realistic and worth doing (technically, financially, and organizationally — detailed in Chapter 2).

- Project Management: the ongoing job of keeping the project on track.

  - Develop a work plan — a schedule that lists and tracks every task the project needs.

  - Staff the project — assign the right people to it.

  - Control and direct the project — monitor progress and correct course as needed.

2. Analysis — “What should the system do for us? Where and when will it be used?”

- Develop analysis strategies — decide the overall approach for figuring out what the system needs to do.

- Gather requirements — collect the specific things the system must be able to do, using methods such as:

  - Interviews — one-on-one conversations with stakeholders to learn their needs.

  - Document analysis — reviewing existing forms, reports, or manuals to understand current processes.

  - Joint Application Development (JAD) — a structured workshop where users, managers, and analysts meet together to define requirements collaboratively (instead of one-on-one).

  - Questionnaires — written surveys sent to a broad group of stakeholders.

  - Observation — watching people do their actual work to see how the process really functions.

3. Design — “How will we build the system?”

- Develop a design strategy — decide the technical approach for building the solution.

- Design architecture and interfaces — plan the system’s overall technical structure and how users will interact with it.

- Develop databases and file specifications — plan how and where data will be stored.

- Develop the program design — plan the actual code/program structure that developers will build from.

4. Implementation — “Build the system!”

- Construct the system — write and assemble the actual code.

- Install the system — put the finished system into the live/production environment.

- Implement a training plan for users — teach the people who will use the system how to use it.

- Establish a support plan — set up how user problems and system issues will be handled after launch.

### Systems Development Methodologies

A methodology = a formalized, repeatable approach to carrying out the SDLC (i.e., a specific “recipe” for how to do planning, analysis, design, and implementation).

Waterfall Development (also called Structured Design)

- Flow: linear phases completed one after another in strict sequence — Plan → Analyze → Design → Implement — with no going backward.

- Planning: extensive and rigid, done entirely upfront before any building starts.

- Change: discouraged; any change requires a formal change control process (an official review/approval procedure before a change can be made).

- Testing: conducted near the end of the project, after most/all of the system is built.

- Customer input: concentrated at the very beginning (defining requirements) and the very end (accepting the finished system).

Agile / Scrum Development

- Uses the Scrum Framework — a specific, lightweight structure of roles, artifacts, and meetings for doing Agile work in short cycles called sprints (a sprint is a fixed, short time period — typically 1–4 weeks — in which the team builds a usable piece of the product).

- Flow: iterative cycles (sprints), typically 1–4 weeks each, repeating until the product is complete.

- Planning: adaptive and continuous; the list of work (the backlog, defined below) evolves as the project goes.

- Change: welcomed and simply folded into upcoming sprints rather than requiring formal approval.

- Testing: continuous — happens during every sprint, not just at the end.

- Customer input: frequent feedback throughout the project, not just at the start/end.

### Choosing Between Scrum and Waterfall

| Choose Scrum when… | Choose Waterfall when… |
| --- | --- |
| Requirements are unclear, complex, or expected to change | Requirements are completely well-defined, stable, and locked in |
| Fast time-to-market and regular delivery of working features matter | Total budget, scope, and final delivery timeline are fixed from day one |
| Customers/stakeholders are available to give continuous feedback | Comprehensive documentation is mandatory (e.g., for legal or regulatory compliance) |
| Building digital products, mobile apps, or SaaS platforms (SaaS = “Software as a Service,” meaning software delivered over the internet rather than installed locally) | Working in hardware, construction, or strict manufacturing environments, where later-stage changes are very costly or physically impossible |

### Object-Oriented Tools

- UML (Unified Modeling Language) — a standardized set of diagram types and symbols used to visually model a software system, from the analysis phase through implementation, so that everyone on the team “speaks the same visual language.”

- Two major diagram groups:

  - Behavior diagrams — diagrams that show what the system does or how it behaves over time:

    - Activity diagrams — show the flow of steps/actions in a process (similar to a flowchart).

    - Use-Case diagrams — show the different ways users (“actors”) interact with the system to accomplish goals.

  - Structure diagrams — diagrams that show what the system is made of:

    - Class diagrams — show the system’s data objects (“classes”), their attributes, and how they relate to each other.

### Project Team Roles & Skills

Team members act as change agents — people who actively drive improvement in how the organization works, rather than just following existing processes.

Broad range of skills required:

- Technical — knowledge of the technology being used.

- Business — understanding of how the organization operates.

- Analytical — the ability to break down problems and figure out solutions.

- Interpersonal — communication and relationship skills for working with people.

- Management — the ability to plan, organize, and coordinate work.

- Ethical — sound judgment about doing the right thing, especially with sensitive data/decisions.

| Role | Responsibilities |
| --- | --- |
| Business Analyst — focuses on the business side of the project | Analyzes key business aspects of the system; identifies how the system will provide business value (the benefit it creates for the organization); designs the new business processes and policies |
| Systems Analyst — the bridge between business needs and technology | Identifies how technology can improve business processes; designs the new technology to fit those processes; designs the information system; ensures the system conforms to IS (Information Systems) standards |
| Infrastructure Analyst — focuses on the technical environment the system runs in | Ensures the system conforms to infrastructure standards (servers, networks, etc.); identifies infrastructure changes required, including networks and cloud infrastructure (computing resources hosted over the internet rather than on local hardware) |
| Change Management Analyst — manages the human side of the transition | Develops and executes a change management plan (a plan for helping people adapt to the new system) and a user training plan |
| Project Manager — oversees the whole effort | Manages the team; develops and monitors the project plan; assigns resources; serves as the primary point of contact for the project |

## CHAPTER 2: Project Initiation & Project Management

### Project Identification and Initiation

- Projects are driven by business needs (a business-related reason or problem that prompts the project — defined further below).

- Identified by: businesspeople, IT people, or — ideally — jointly by both, so the project addresses a real business problem and is technically sound.

- Project sponsor — the person who believes in the system and wants it to succeed; normally a businessperson (not an IT person); should have the organizational authority to actually move the project forward (approve budget, resolve roadblocks, etc.).

### Elements of a System Request

A system request is the formal document used to ask an organization to commit time and money to a project. Its key elements:

| Element | Definition | Examples |
| --- | --- | --- |
| Project sponsor | The person who initiates the project and serves as the primary point of contact for the business side | Members of the Finance Department, VP of Marketing, a Sales/Marketing/Account Manager, the Steering Committee Chair (head of the group that oversees project approvals), CEO/CFO/CMO |
| Business need | The business-related reason prompting the project | Increase sales, improve market share (the company’s share of total sales in its industry), improve access to information, improve customer service, decrease product defects, streamline the supply acquisition process |
| Business requirements | The business capabilities the system will need to have | Provide online access to information, capture customer demographics (statistical data about customers, e.g., age/location), include product search capabilities, produce management reports, include online user support |
| Business value | The benefits the organization can expect from the project | Tangible (measurable in concrete numbers): a 3% increase in sales, a 1% increase in market share, reduction of headcount by 5 FTEs (Full-Time Employees — a unit for measuring staffing, where one FTE = one person working full-time), $150,000 in savings by relocating data to the cloud. Intangible (real but hard to measure precisely): improved customer service |
| Special issues | Anything else relevant to the implementation decision | A government-mandated deadline, a system needed in time for the Christmas shopping season, top-level security clearance needed by the project team |

### Feasibility Analysis

Feasibility analysis guides the organization in deciding whether to proceed with a project, and identifies the risks that would need to be managed if it’s approved. Three major components:

1. Technical Feasibility — “Can we build it?” (can the team realistically build this with the skills and technology available?)

- User/Analyst familiarity with the application — how well the team knows this type of system; less familiarity generates more risk.

- User/Analyst familiarity with the technology — how well the team knows the specific tools/platform being used; less familiarity generates more risk.

- Project size — larger projects carry more risk (more can go wrong, more coordination needed).

- Compatibility — how well the new system needs to work with existing systems; difficult integration increases risk.

2. Economic Feasibility — “Should we build it?” (does the financial payoff justify the cost?)

- Development costs — the cost to analyze, design, and create the new system.

- Annual operating costs — the ongoing yearly cost to run the system once it’s live.

- Annual benefits — cost savings and revenues the system generates each year.

- Intangible costs and benefits — non-financial effects, like whether work will be easier or customers/employees happier.

- This analysis is called a cost-benefit analysis — a comparison of a project’s total costs against its total benefits, often used to calculate the break-even point (the point in time at which the cumulative benefits of a project equal its cumulative costs — i.e., when the project “pays for itself”).

3. Organizational Feasibility — “If we build it, will they come?” (will the organization actually adopt and support it?)

- Stakeholder analysis — the process of identifying everyone with a stake in the project and the role each plays:

  - Project champion(s) — the person/people who pay for the project.

  - Project sponsor — provides requirements (see definition above).

  - Senior management — leadership who can support or block the project.

  - Users — the people who will actually use the system day-to-day.

  - Others — any other affected party.

- Is the project strategically aligned with the business (does it support the organization’s broader goals)?

### Project Selection

- Project portfolio management — a process that optimizes which projects an organization selects and in what order (sequencing), so the mix of projects best supports business goals.

- Business goals are expressed in terms of:

  - Quantitative economic measures — hard numbers, like expected ROI (Return on Investment, i.e., the financial gain relative to what was spent).

  - Business strategy goals — how the project supports the company’s broader direction.

  - IT strategy goals — how the project supports the technology department’s broader direction.

- Once selected, projects enter the project management process (the ongoing planning/tracking work described below).

### Estimating Project Timeframes

- Note: Scrum combines the Analysis and Design phases into one combined effort (~55% of the project timeline per the course slide), instead of treating them as two separate sequential phases like Waterfall does.

### Creating and Managing the Work Plan

- A work plan is a dynamic (regularly updated) schedule that records and tracks all tasks to be accomplished over the course of the project.

- Created after a project manager has a general idea of the project’s size and rough schedule.

- The work plan is usually the main item tracked inside project management software (e.g., Microsoft Project).

Sample Task fields (the pieces of information tracked for each task in the work plan):

- Task name — what the task is called.

- Start date / Completion date — when it begins and is due.

- Person assigned to the task — who is responsible.

- Deliverable(s) — the tangible output the task produces.

- Completion status — whether it’s done, in progress, etc.

- Priority — how urgent/important it is.

- Resources needed — tools or materials required (e.g., spreadsheet software).

- Estimated time vs. Actual time — planned effort vs. what it really took (used to improve future estimates).

Identifying Tasks — two approaches:

- Top-down approach — start by identifying the highest-level tasks, then break each one into increasingly smaller units.

- Methodology-based approach — use a standard list of tasks provided by prior projects or industry standards, rather than building the list from scratch.

Displaying the Work Plan:

- Work Breakdown Structure (WBS) — a hierarchical chart that displays all the tasks and related information (like duration and dependencies) from the work plan, broken down from big tasks into smaller sub-tasks.

- Gantt Chart — a horizontal bar chart showing each task plotted against a timeline, so you can see start/end dates and overlaps at a glance; created automatically when the WBS is entered into Microsoft Project.

Scope Management

- Scope creep — happens when new requirements are added to the project after the original project scope (the defined boundaries of what the project will and won’t include) was defined and “frozen” (locked in), often causing budget/timeline overruns.

### Staffing the Project

- Determine the average number of people needed = total person-months of effort (a unit meaning one person working for one month) divided by the optimal schedule length.

- Important principle: adding more people to a late project will not reduce the schedule — often called Brooks’s Law — because new people need time to get up to speed and add communication overhead.

- Create a staffing plan, which includes:

  - Roles required for the project.

  - Reporting structure — who reports to whom.

### Motivation

- Use monetary rewards (pay, bonuses) cautiously — they can backfire or lose effectiveness over time.

- Favor intrinsic rewards — rewards that come from the work itself rather than external pay, such as:

  - Recognition — being acknowledged for good work.

  - Achievement — the satisfaction of accomplishing something.

  - The work itself — finding the work inherently engaging.

  - Responsibility — being trusted with meaningful ownership.

  - Advancement — opportunities to grow into bigger roles.

  - The chance to learn new skills.

### Managing Risk

- (Title-only slide in the deck — no detail provided yet. Add specifics once lecture notes/readings on risk management are available.)

## SCRUM — Combined from Core_Scrum.pdf and CIS454_PP_Scrum_Ch_1.pptx

### Foundations

Agile Manifesto — a short foundational document (written by a group of software developers) that lays out four core values favored by all Agile approaches, including Scrum:

- Individuals and interactions over processes and tools — trusting people and how they work together matters more than rigid procedures.

- Working software over comprehensive documentation — a functioning product matters more than extensive paperwork about it.

- Customer collaboration over contract negotiation — working with the customer throughout matters more than locking everything into an upfront contract.

- Responding to change over following a plan — adapting to new information matters more than rigidly sticking to the original plan.

Scrum’s Five Values:

- Focus — concentrating on only a few things at a time so the team works well together.

- Courage — the confidence to take on bigger challenges because the team has support.

- Openness — being willing to express how things are going, including problems.

- Commitment — dedication to success that comes from having real control over the work.

- Respect — mutual regard built through working together and sharing both successes and failures.

The Essence of Scrum (course slide):

- The team is given clear goals.

- The team organizes itself around the work (self-organizes — decides internally how to divide and do the work, without being told exactly how by a manager).

- The team regularly delivers the most valuable features.

- The team receives feedback from people outside it.

- The team reflects on its way of working in order to improve.

- The entire organization has visibility (clear insight) into the team’s progress.

- The team and management honestly communicate about progress and risks.

### Scrum Roles

Product Owner

- The single individual responsible for maximizing the value of the product delivered by the desired date.

- Manages and prioritizes the Product Backlog (defined below — the master list of everything that might be built).

- Manages the flow of work into the team by selecting and refining backlog items.

- Gathers requirements and works on a shared vision for the product with the team.

- Accepts the software at the end of each iteration (sprint) — confirms it meets expectations.

- Manages the release plan — the plan for when/how finished work goes out to real users.

- Owns the profitability of the project, i.e., its ROI (Return on Investment).

- May be supported by others but must ultimately be a single accountable person.

ScrumMaster / Scrum Master

- A “servant leader” — a leadership style focused on serving and supporting the team’s needs, rather than directing them top-down; manages the process, not the product.

- Must understand the Scrum framework well enough to train others in its details.

- Removes impediments (obstacles blocking the team’s progress), whether they come from inside or outside the team.

- Helps the Product Owner learn to create and maintain the Product Backlog.

- Helps the Development Team find technical practices to reach the Definition of Done (defined below).

- Socializes Scrum — helps people outside the team understand how Scrum works and how to interact with the team productively.

- Fosters self-organization and protects the team from distractions.

- Keeps meetings time-boxed (a time-box is a strict, fixed maximum duration for a meeting or activity — once time is up, the meeting ends regardless of whether the discussion is finished).

Development Team

- A self-organizing, cross-functional group — meaning that, collectively, the team members possess all the skills needed to deliver the product (so no outside specialist is required).

- Expected to work full-time on the project.

- Forecasts how much work they can complete in a sprint and decides how to do it (as opposed to the Product Owner, who decides what to do).

- Responsibilities: estimate the size of backlog items, commit to delivering increments of working software (and actually deliver them), track their own progress.

- Self-organizing but still accountable to the Product Owner for delivering as promised.

- No dictated leadership hierarchy within the team — everyone is a peer.

- Can include: developers, testers, analysts, architects, writers, designers, and even users.

Key distinction: the Product Owner manages the product (and its ROI); the Scrum Master manages the process; the Team manages itself. Together these three roles split up the responsibilities that a traditional single project manager would otherwise hold.

Self-organized teams (course emphasis):

- Highly disciplined, given full autonomy, and correspondingly carry greater responsibility for delivery.

- Encouraged to take reasonable risks and learn through failure and self-reflection (looking back at their own performance to improve).

- Encouraged to take ownership of their work.

- No appointed leaders beyond the Product Owner and Scrum Master.

### Scrum Artifacts

An artifact, in Scrum, just means a key work product/document the framework produces to keep everyone informed.

| Artifact | Definition |
| --- | --- |
| Product Backlog | The ordered (prioritized) list of everything that might be needed in the product; the single source from which all requirements flow — every feature, bug fix, or piece of work traces back to a backlog item. Each item includes a description and an estimate. Anyone (Product Owner, team, or other stakeholders) can add items. It’s a “living document” that requires ongoing refinement/“grooming” (see below). Often written as user stories — short descriptions of a feature from the end user’s point of view, traditionally on 4×6 index cards. |
| Sprint Backlog | The set of refined Product Backlog items chosen for development in the current sprint, plus the team’s plan for how to accomplish them; reflects the team’s forecast of what they can complete. Tracked on a Sprint task board (a visual board showing tasks and their status, e.g., “to do / in progress / done”). |
| Product Increment | The most important Scrum artifact — a working, integrated, potentially shippable piece of the product produced at the end of every sprint. Must meet the Definition of Done (below) and be acceptable to the Product Owner. |

Additional visibility tools: burn charts, task boards (extra artifacts the team creates as needed to keep progress transparent).

- Sprint Burndown Chart — a chart graphing the team’s remaining work (in stories or tasks) over the course of the current sprint, making it easy to see whether they’re on track to meet their sprint commitment.

- Product Burndown Chart — a chart measuring the rate at which working, tested features are delivered over the life of the entire product (i.e., across many sprints).

Definition of Done

- The shared understanding, agreed on by the whole Scrum Team, of exactly what “done” means for a Product Increment (e.g., coded, tested, integrated, documented).

- Different for every team, and it typically expands and becomes more stringent as the team matures.

- Must always include: the increment is of high enough quality to be shippable (ready to be released to real users) immediately, if the Product Owner chooses to do so.

- The increment must include the functionality of all previous increments and be fully tested so everything still works together.

### Scrum Activities / Meetings

All Scrum meetings are time-boxed (fixed maximum duration — see definition above).

1. Product Backlog Refinement (“grooming”) — an ongoing activity throughout the project, not a one-time meeting

- Keep the Product Backlog ordered (prioritized).

- Remove or demote items that no longer seem important.

- Add or promote items that arise or become more important.

- Split large items into smaller ones; merge small items into larger ones.

- Estimate items (assign a rough size/effort to each).

- Prepare upcoming items so they have clear business value, can fit within a single sprint, and are understood by everyone.

2. Sprint Planning — recommended time-box: 2 hours per week of sprint length

- Part 1 — What will be done (Requirements Gathering):

  - The Product Owner presents ordered Product Backlog items to the team.

  - The team asks questions to reach a shared understanding sufficient to commit to delivering the feature.

  - The team alone decides how many items to take on — the Product Owner (or anyone else) cannot push extra work onto them.

  - Often produces a Sprint Goal — a short statement of the overall purpose of the sprint, helping the team focus on the essence of what’s needed rather than small details.

  - The team commits to what they believe they can deliver as “running, tested features” (working software that has actually been tested, not just written).

- Part 2 — How the work will be accomplished (Design):

  - The team collaborates to create a high-level design for the features they’ve committed to.

  - Produces the Sprint Backlog (defined above) — the specific list of tasks needed to turn commitments into working features.

  - The team may still ask clarifying questions about requirements during this part.

  - Design is emergent (it develops and changes as work proceeds, rather than being fully planned upfront) — it’s normal not to finish the design perfectly in this meeting, and the team will discover more tasks during the sprint itself.

3. Development / The Sprint

- Fixed length: 1–4 weeks (shorter preferred).

- The self-organizing team builds the Product Increment according to the Sprint Backlog and the Definition of Done.

4. Daily Scrum / Daily Stand-up — time-box: 15 minutes (course slide also separately describes a Daily Stand-up of just 1–2 minutes per person)

- Happens at the same time and place every day.

- Each team member answers three questions:

  - What I accomplished since the last meeting.

  - What I plan to accomplish before the next one.

  - What is impeding (blocking) my progress.

- It is not a status report to management, the Product Owner, or the Scrum Master — it’s a synchronization meeting for the Development Team itself.

- No deep discussion happens during the meeting itself; any needed follow-up conversations happen right after.

- Only Scrum Team members (Dev Team, Scrum Master, Product Owner) speak; other interested people may observe silently.

- Impediments raised are meant to be resolved quickly (“bulldozed”).

5. Sprint Review — time-box: 1 hour per week of sprint length

- The Scrum Team demos and inspects the Product Increment completed during the sprint.

- Stakeholders (anyone with a “stake,” or interest, in the outcome) are encouraged to attend and give input.

- The group discusses what they observed, new product ideas, and the state of the Product Backlog, including possible future completion dates.

- The Product Owner makes the final decisions about the future direction and updates the Product Backlog accordingly.

- Described in the course slide as gathering feedback from “the whole world” — i.e., as broad an audience as makes sense.

6. Sprint Retrospective — time-box: 1 hour per week of sprint length

- Happens after the Sprint Review; attended only by Scrum Team members (not outside stakeholders).

- Focuses on process, not the product itself: how well the team worked together, and whether their skills, practices, and tools are serving them well.

- Operates on the assumption that everyone did their best — the question is whether different skills, practices, or tools are needed to succeed going forward.

- Produces a plan for improving in the next sprint, while staying within the Scrum framework.

### The Scrum Cycle (summary flow)

Product Backlog → Refinement (ongoing) → Sprint Planning (Part 1: what; Part 2: how) → Sprint Backlog → Development (with Daily Scrums) → Product Increment → Sprint Review → Sprint Retrospective → repeat for the next sprint.

## Quick-Reference: Time-Boxes Cheat Sheet

| Meeting | Time-Box | What it’s for |
| --- | --- | --- |
| Sprint | 1–4 weeks | The full work cycle that produces one Product Increment |
| Sprint Planning | ≤2 hrs per week of sprint | Deciding what to build and how |
| Daily Scrum | ≤15 minutes | Daily team sync on progress and blockers |
| Daily Stand-up (course variant) | 1–2 minutes per person | A shorter version of the daily sync |
| Sprint Review | 1 hr per week of sprint | Demoing the increment and gathering feedback |
| Sprint Retrospective | 1 hr per week of sprint | Reflecting on team process, not the product |

## Notes / Gaps to Fill Later

- “Managing Risk” (Ch2, slide 33) was a title-only slide — add detail once lecture notes/readings on this are provided.

- “Reporting Structures” (Ch2, slide 31) and the “Sample Cost-Benefit Analysis” / “Equations for Cost-Benefit Analysis” (slides 14–16) were diagram/image-based slides — add specifics once available as text, or describe the diagrams and I’ll write them up.

Send new chapters, slides, readings, or notes any time and I’ll fold them into this guide, keeping the same inline-definition style.